## Project Plan
WBS ID | Phase | Task | Owner | Start Date | End Date | Dependency | Status
1.1 | Initiation | Define business problem and project objectives | Project Manager | 8/102026 | 2016-08-12 |  | Complete
1.2 | Initiation | Identify project stakeholders | Project Manager | 2026-08-10 | 2026-08-12 | 1.1 | Complete
1.3 | Initiation | Define High-level project scope | PM / Business sponsor | 2026-08-12 | 2026-08-14 | 1.1 | In progress
1.4 | Initiation | Identify project team and roles | Project Manager | 2026-08-12 | 2026-08-14 | 1.2 | In progress
1.5 | Initiation | Conduct project kickoff meeting | Project Manager | 2026-08-18 | 2026-08-17 | 1.3 1.4 | Not started
2.1 | Discovery | Conduct stake holder requirement workshops | PM / Business analyst | 2026-08-18 | 2026-08-21 | 1.5 | Not started
2.2 | Discovery | Document current incident management process | Business Analyst | 2026-08-18 | 2026-08-21 | 1.5 | Not started
2.3 | Discovery | Identify pain paoints and process gaps | PM / Business Team | 2026-08-20 | 2026-08-24 | 2.2 | Not started
2.4 | Discovery | Define future-state ServiceNow requirements | BA / ServiceNow Lead | 2026-08-24 | 2026-08-28 | 2.1, 2.3 | Not started
2.5 | Discovery | Identify integration and data migration needs | Technical Lead | 2026-08-24 | 2026-08-28 | 2.1 | Not started
2.6 | Discovery | Prioritize requirements | PM / Product owner | 2026-08-28 | 2026-08-31 | 2.4 | Not started
2.7 | Discovery | Obtain requirements sign-off | Business sponsor | 2026-09-01 | 2026-09-02 | 2.4, 2.6 | Not started
3.1 | Design | Review approved business requirements | PM / ServiceNow Lead | 2026-09-03 | 2026-09-03 | 2.7 | Not started
3.2 | Design | Design future-satte incident management workflow | ServiceNow Lead/ Business Team | 2026-09-03 | 2026-09-08 | 2.7 | Not started
3.2 | Design | Define incident categories, prioroties and assignment groups | Business Lead/ ServiceNow Lead | 2026-09-04 | 2026-09-09 | 3.1 | Not started
3.4 | Design | Define roles, permissions, and approval workflows | ServiceNow Lead/ Security Team | 2026-09-08 | 2026-09-10 | 3.1 | Not started
3.5 | Design | Finalize integration and data migration design | Technical Lead | 2026-09-08 | 2026-09-11 | 2.5 | Not started
3.6 | Design | Review solution design with stakeholders | Project Manager | 2026-09-14 | 2026-09-15 | 3.2, 3.3, 3.4, 3.5 | Not started
3.7 | Design | Obtain solution design approval | Business sponsor / IT Leadership | 2026-09-16 | 2026-09-16 | 3.6 | Not started
4.1 | Build | Configuration incident management workflow in DEV | ServiceNow Developer | 2026-09-17 | 2026-09-23 | 3.7 | Not Started
4.2 | Build | Configure categories priorities, assignment groups, SLAs | ServiceNow Developer | 2026-09-17 | 2026-09-23 | 3.7 | Not Started
4.3 | Build | Configure roles, permisssions, and approval roles | ServiceNow Developer / Security team | 2026-09-21 | 2026-09-25 | 3.4,3.7 | Not Started
4.4 | Build | Develop required integrations |  | 2026-09-21 | 2026-10-02 | 3.5,3.7 | Not Started
4.5 | Build | prepare Data migration scripts and mapping | Data Team/ DBA | 2026-09-21 | 2026-10-02 | 3.5,3.7 | Not Started
4.6 | Build | Perform developer/unit testing | ServiceNow Development Team | 2026-09-28 | 2026-10-05 | 4.1.4.2.4.3 | Not Started
4.7 | Build | Track defects and configuration fixes | PM/ Development Lead | 2026-09-29 | 2026-10-07 | 4.6 | Not Started
4.8 | Build | Promote approved configuration from DEV tto TEST | Release Manager/ ServiceNow team | 2026-10-08 | 2026-10-08 | 4.6.4.7 | Not Started
5.1 | Testing | Prepare system and integration test plan | QA Lead /PM | 2026-10-09 | 2026-10-12 | 4.8 | Not Started
5.2 | Testing | execute system testing in TEST environment | QA team | 2026-10-13 | 2026-10-19 | 5.1 | Not Started
5.3 | Testing | Execute integration testing | QA / integration team | 2026-10-13 | 2026-10-20 | 4.4,5.1 | Not Started
5.4 | Testing | Log and prioritize defects | QA Lead /PM | 2026-10-13 | 2026-10-21 | 5.2,5.3 | Not Started
5.5 | Testing | Resolve and restest defects | Development / QA team | 2026-10-16 | 2026-10-23 | 5.4 | Not Started
5.6 | UAT | Prepare UAT scenarios and test data | Business Lead /QA | 2026-10-20 | 2026-10-23 | 5.2 | Not Started
5.7 | UAT | Conduct UAT with Business users | Business Users / PM | 2026-10-26 | 2026-10-30 | 5.5,5.6 | Not Started
5.8 | UAT | Track and resolve UAT defects | PM/ Development team | 2026-10-26 | 2026-11-03 | 5.7 | Not Started
5.9 | UAT | Obtain formal UAT sign-off | Business sponsor | 2026-11-04 | 2026-11-04 | 5.8 | Not Started
6.1 | Training | Identify impacted user groups and training needs | PM /Business Lead | 2026-10-26 | 2026-11-04 | 5.6 | Not Started
6.2 | Training | Develop ServiceNow training materials and job aids | Training Lead/ ServiceNow Team | 2026-10-29 | 2026-11-05 | 6.1 | Not Started
6.3 | Change Mgmt | Prepare stakeholder communication and change plan | PM/ Change Manager | 2026-10-29 | 2026-11-04 | 6.1 | Not Started
6.4 | Training | Conduct train-the-trainer sessions | Training Lead | 2026-11-05 | 2026-11-06 | 6.2 | Not Started
6.5 | Training | Conduct end-user training | Training Lead | 2026-11-09 | 2026-11-13 | 6.4 | Not Started
6.6 | Readiness | Track training completion and user readiness | PM/ Training Lead | 2026-11-09 | 2026-11-16 | 6.5 | Not Started
6.7 | Change Mgmt | Send go-live communication and support instructions | PM/ Communication lead | 2026-11-16 | 2026-11-18 | 6.3,6.6 | Not Started
6.8 | Readiness | Obtain business readiness confirmation | Business Sponsor /PM | 2026-11-18 | 2026-11-18 | 5.9.6.6 | Not Started
7.1 | Deployment | Prepare production deployment plan | PM / Release Manager | 2026-11-09 | 2026-11-13 | 5.9 | Not Started
7.2 | Deployment | Prepare implementation and rollback procedures | ServiceNow Lead / Release Manager | 2026-11-09 | 2026-11-13 | 5.9 | Not Started
7.3 | Readiness | Conduct go-live readiness review | PM | 2026-11-16 | 2026-11-17 | 5.9,6.6 | Not Started
7.4 | Deployment | Submit production change request / CAB approval | Change Manager/ PM | 2026-11-16 | 2026-11-19 | 7.1,7.2 | Not Started
7.5 | Readiness | Confirm production access, integrations, support, and monitoring readiness | Technical Lead/ PM | 2026-11-18 | 2026-11-20 | 7.3 | Not Started
7.6 | Deployment | Obtain final go/no-go approval | Sponsor / IT Leasdership/ PM | 2026-11-20 | 2026-11-20 | 6.8,7.4,7.5 | Not Started
7.7 | Deployment | Deploy ServiceNow solution to PROD | Service Now / Release team | 2026-11-21 | 2026-11-21 | 7.6 | Not Started
7.8 | validation | Perform production smoke testing | ServiceNow / QA / Business Team | 2026-11-21 | 2026-11-21 | 7.7 | Not Started
7.9 | Deployment | Send go-live confirmation to stakeholders | PM | 2026-11-21 | 2026-11-21 | 7.8 | Not started
8.1 | Hypercare | Monitor production incidents and user-reported issues | PM / Support Team | 2026-11-23 | 2026-12-04 | 7.9 | Not started
8.2 | Hypercare | Conduct daily hypercare review meetings | PM | 2026-11-23 | 2026-12-04 | 7.9 | Not started
8.3 | Hypercare | Track and prioritize production defects | PM / ServiceNow Lead | 2026-11-23 | 2026-12-04 | 8.1 | Not started
8.4 | Hypercare | Provide user office hours / support sessions | Business Lead / Training Team | 2026-11-23 | 2026-12-04 | 7.9 | Not started
8.5 | Hypercare | Resolve critical post-production issues | ServiceNow / Technical Team | 2026-11-23 | 2026-12-04 | 8.3 | Not started
8.6 | Hypercare | Review adoption, ticket trends, and SLA performance | PM / ServiceNow Lead | 2026-11-30 | 2026-12-04 | 8.1 | Not started
8.7 | Transition | Complete knowledge transfer to support team | ServiceNow Lead / Support Lead | 2026-12-02 | 2026-12-04 | 8.5 | Not started
8.8 | Transition | Obtain hypercare exit approval | PM / Business Sponsor | 2026-12-04 | 2026-12-04 | 8.5,8.7 | Not started
9.1 | Closure | Confirm all project deliverables are completed | PM | 2026-12-07 | 2026-12-08 | 8.8 | Not started
9.2 | Closure | Review and close remaining RAID items | PM / Workstream Leads | 2026-12-07 | 2026-12-09 | 8.8 | Not started
9.3 | Closure | Confirm transition to steady-state support | PM / Support Lead | 2026-12-08 | 2026-12-09 | 8.7 | Not started
9.4 | Closure | Conduct lessons learned session | PM / Project Team | 2026-12-09 | 2026-12-09 | 9.1 | Not started
9.5 | Closure | Document project outcomes and lessons learned | PM | 2026-12-09 | 2026-12-10 | 9.4 | Not started
9.6 | Closure | Obtain final business acceptance | Business Sponsor | 2026-12-10 | 2026-12-10 | 9.1,9.3 | Not started
9.7 | Closure | Close project and archive documentation | PM | 2026-12-11 | 2026-12-11 | 9.2,9.5,9.6 | Not started

## RACI Matrix
Activity | Project Manager | Business Sponsor | Business Analyst | ServiceNow Lead | Developer | QA Team | Business Users | Release/Change Manager
Project kickoff | R | A | C | C | I | I | I | I
Requirements gathering | A | C | R | C | I | I | C | I
Solution design | C | I | C | A/R | C | I | C | I
ServiceNow configuration | I | I | C | A | R | C | I | I
System testing | C | I | I | C | C | A/R | I | I
UAT | A | I | C | C | I | C | R | I
Training & readiness | A/R | C | C | C | I | I | C | I
Go-live readiness | R | A | I | C | I | C | C | C
CAB / Change approval | C | I | I | C | I | I | I | A/R
Production deployment | C | I | I | C | R | C | I | A
Hypercare | A/R | I | C | C | R | C | C | I
Project closure | R | A | C | C | I | I | I | I
RACI Legend | C A/R R: Meaning
R | C A/R R: Responsible – performs the work
A | C A/R R: Accountable – owns the outcome
C | C A/R R: Consulted – provides input
I | C A/R R: Informed – kept updated

## Status report
Section | Example
Project | ServiceNow Incident Management Implementation
Reporting Period | Week of 11/16/2026
Overall Status | Green
Project Manager | Sree
Current Phase | Deployment / Go-Live Readiness
Accomplishments | UAT completed; business sign-off obtained; end-user training completed
Upcoming Activities | CAB approval; go/no-go meeting; production deployment
Key Risks | UAT resource availability; production integration readiness
Key Issues | None critical
Key Dependencies | CAB approval and production access
Decisions Needed | Final go/no-go approval
Overall Comment | Project remains on track for planned production go-live