## Sheet1
ID | Type | Description | Impact | Probability | Owner | Mitigation/ Action | Due Date | Status
R-001 | Risk | Business teams may not provide requirements on time | High | Medium | Project Manager | Schedule requirement workshops and track outstanding items | 2026-08-21 | Open
A-001 | Assumption | Required ServiceNow licenses will be available before development begins | Medium |  | ServiceNow Lead | Validate licenses during project initiation | 2026-08-14 | Open
I-001 | Issue | Current incident categories contain duplicate and inconsistent values | High |  | Business Lead | Review and approve standardized category list | 2026-08-18 | In progress
D-001 | Dependency | SSO integration must be completed before UAT | High |  | IAM Team | Track IAM integration milestone in project plan | 2026-09-18 | Open
R-002 | Risk | UAT users may not be available during planned testing | High | Medium | Project Manager | Confirm UAT resources early and get manager commitment | 2026-09-11 | Open
R-003 | Risk | Data Migration may contain incomplete or duplicate records | High | Medium | Data Lead | Perform data profiling and trial migration before production | 2026-09-04 | Open
I-002 | Issue | Bussiness and technical teams disagree on incident priority definitions | Medium |  | Business Lead | Conduct workshop and obtain approved priority matrix | 2026-08-28 | In progress
D-002 | Dependency Production deployment requires Change Advisory Board approval |  | High |  | PM / Change Manager | Submit change request before CAB cutoff date | 2026-09-25 | Open